# Roadmap

Jul 30, 2024

| Project | Status | Related files | Notes | Date |  |
| --- | --- | --- | --- | --- | --- |
| Finish RE courses (Rohit) | Complete | File |  |  |  |
| Get 10-15 Student discovery surveys from mutual friends (Rohit and Mihir). | Complete | File |  |  |  |
| Get 25-30 Student discovery surveys (Rohit and Mihir) | Complete | File |  |  |  |
| Service landlords and a few sublets (Rohit) | Cancelled | File |  |  |  |
| Begin Bubble IO course (Rohit) | Cancelled | File |  |  |  |
| Begin Roommate Surveys 20-30 people STRANGERS (Rohit and Mihir) | Triaged | File |  |  |  |
| Service landlord clients (Rohit) | Cancelled | File |  | Jun 1, 2024 |  |
| Begin videos of certain areas (Rohit and Mihir) | Complete | File |  | Jun 1, 2024 |  |
| Brainstorm changes to platform based off roommate matching (Mihir) | Triaged | File |  | Jun 1, 2024 |  |
| Finalize Landlord survey questions | Complete | Customer Discovery Questions (Landlords) |  | Date |  |
| Brainstorm changes to platform based off student discovery (Mihir) | Complete | File |  | Jun 1, 2024 |  |
| Study and Take RE Exam (Rohit) | In progress | File |  |  |  |
| Design for new platform (Rohit and Mihir) | In progress | Feedback to Website Possible Template | We are going with TinyTemplate. Drawing sketch. | Jun 1, 2024 |  |
| File Legal Requirements | In progress | C-Corp Choices |  | Date |  |
| Finish Landlord surveys | In progress | Customer Discovery Questions (Landlords) |  | Aug 31, 2024 |  |
| Brainstorm Map (Rohit) | In progress | Map of Different Regions | This is the map of the different regions of campus. | Oct 31, 2024 |  |
| Finish editing campus tour videos of areas (Rohit and Mihir) | In progress | File |  | Oct 31, 2024 |  |
| Record Intro for Campus Tour | Not started | File | Contingent on “Brainstorm Map” and “Campus Tour Videos” | Date |  |
| Student Interview Videos | Not started | Questions for interview videos | Aug 26 Week | Oct 31, 2024 |  |
| Convert Design to Bubble IO Page | Not started | File |  | Aug 31, 2024 |  |
| Brainstorm marketing ideas (Mihir) | Not started | File |  | Aug 31, 2024 |  |
| Sign with brokerage | Not started | File |  | Date |  |
| Finalize marketing strategy | Not started | File |  | Date |  |
| Finish Map (Rohit and Mihir) | Not started | File |  | Date |  |
| MVP Launch | Not started | File |  | Oct 1, 2024 |  |
| Start marketing to students FREE (Rohit and Mihir) | Not started | File |  | Oct 1, 2024 |  |
| Start marketing to landlords | Not started | File |  | Date |  |
| Begin marketing to students PAID (Rohit and Mihir) | Not started | File |  | Date |  |